## Dashboard
PROJECT REBOOT — PROJECT HEALTH DASHBOARD
Project | SmartSpend | Project Area | Status | Notes | Project Area | Status Count
Project Type | Digital Product Launch | Scope | At Risk | Requirements require prioritisation | At Risk | 4
Snapshot | Day 20 of 30 | Timeline | At Risk | Project is behind original schedule | Needs Attention | 2
Overall Status | At Risk | Budget | At Risk | Resource pressure may increase costs
Recovery Progress | 67% | Resources | At Risk | Engineering resources are limited
Open Issues | 5 | Stakeholders | Needs Attention | Alignment needs improvement
High-Priority Risks | 3 | Compliance | Needs Attention | Approval required before launch
Active Dependencies | 5
Pending Change Requests | 1

## Risks
ID | Risk | Probability | Impact | Rating | Owner | Status
R-01 | Further timeline delays | High | High | High | PM | Open
R-02 | Scope creep from new requirements | High | High | High | PM / PO | Open
R-03 | Limited engineering resources | Medium | High | High | PM / ENG | Open
R-04 | Compliance approval delay | Medium | High | High | COMP | Open
R-05 | Delayed stakeholder decisions | Medium | Medium | Medium | PM | Open
R-06 | UX/UI work takes longer than planned | Medium | Medium | Medium | UX | Open
R-07 | Testing identifies critical defects | Medium | High | High | ENG | Open

## Issues
ID | Issue | Impact | Priority | Owner | Status
I-01 | Project is behind the original schedule | Launch timeline affected | High | PM | Open
I-02 | Requirements are changing during execution | Scope and timeline affected | High | PM / PO | Open
I-03 | Stakeholders are not fully aligned | Decisions may be delayed | High | PM | Open
I-04 | Budget is under pressure | Additional resources may be difficult to obtain | Medium | PM / FIN | Open
I-05 | Limited resources are available | Critical activities may be delayed | High | PM / ENG | Open

## Milestones
Milestone | Target Day | Status
Project Health Assessment Complete | 5 | Complete
Scope & Priorities Approved | 10 | Complete
Recovery Progress Review | 19 | Complete
Critical Activities Recovered | 23 | Upcoming
Launch Readiness Assessment | 29 | Upcoming
Management Review | 30 | Upcoming

## Change Requests
ID | Request | Scope Impact | Timeline Impact | Resource Impact | Status
CR-001 | Personalised monthly spending summary + social sharing | High | Medium-High | Medium | Pending Approval